## Tool 36 - Intro
Tool 36: Risk management – Introduction and instructions
Each cross-border healthcare project requires thorough risk management to ensure the success of a project and prevent or mitigate potential project risks (see project-specific challenges (see Table 42, Table 36, Table 31, Table 44 and Table 46). For the purpose of the Cross-border Manual & Tools, information on risk management refers to the pre-assessment, monitoring and post-assessment of potential risks associated with the project planning phase [100-102]. To put it simply, risk management involves three basic steps: 1.) identifying risks, 2.) assessing risks (see Tool 37) and 3.) dealing with risks (see Tool 38). All partners should be involved in the identification of risks, which can be done by conduct-ing a very basic brainstorming session. The aim is to raise the partners’ awareness of the risks and to identify as many risks as possible. Partners should make sure they consider risks related to different countries, legislative systems, sectors and types of organisa-tions.
Risk management pre-assessment
Introduction
The purpose of the risk management pre-assessment is to identify potential risks associated with the planned project before the start of the project and to define potential prevention and mitigation strategies for the listed risks. Prevention strategies help to prevent identified risks from occurring in the course of the project, while mitigation strategies help to reduce their impact on the project if they do occur. Pre-assessment of risks and underlying strategies help ensure a rapid response to events that occur in order to exercise control at the earliest stage.
Instructions for the risk management pre-assessment
1. Please turn to the Risk management template (Tool 38) and fill in the potential risks associated with your project in the first column of the risk definition ('risk').
2. Please rate each of the listed risks by categorising them using the Risk management matrix (Tool 37) and fill in the impact, probability, level and rating key you attribute to each risk in the Risk management template (Tool 38).
3. Define the responsible stakeholder and state the organisation and name. This helps you to distinguish between the responsibilities of the various stakeholders involved in the project and indicate/communicate their respective responsibilities.
4. Develop potential prevention and mitigation strategies. The overall coordinator of the project is tasked with ensuring execution of prevention and mitigation strategies. | Inspired by following sources:
5. Inform stakeholders and responsible persons (responsible and executing persons) about the current status quo and request written confirmation of risk management pre-assessment. | EC, Project Cycle Management Guidelines, Vol 1, March 2004
Source: GOE FP based on [1-3]
References
[1] | European Commission. Project Cycle Management Guidelines. Brussels, 2004.
[2] | Datta S, Mukherjee S, editors. Developing a risk management matrix for effective project planning--an empirical study. 2001: Project Management Institute.
[3] | Chapman C, Ward S. Project risk management: processes, techniques, and insights: Wiley; 2003.

## Tool 37 -Risk Management Matrix
Tool 37: Risk management matrix
Once risks have been identified, they need to be assessed on the basis of their probability of occurrence and their impact on the project. This can be done by using a risk assessment matrix (see Tool 37). A suitable risk management strategy (including risk prevention and risk mitigation) needs to be developed according to the given rating (low, medium, high risk).
Risk Rating Key |  | LOW | MEDIUM | HIGH | EXTREME
|  | ACCEPTABLE | ALARP (as low as reasonably pracicable) | GENERALLY UNACCEPTABLE | INTOLERABLE
|  | OK TO PROCEED | TAKE MITIGATION EFFORTS | SEEK SUPPORT | PLACE EVENT ON HOLD
Risk impact on Project
|  | ACCEPTABLE | TOLERABLE | UNDESIRABLE | INTOLERABLE
|  | Little to no effect on project | Effects are felt, but not critical to outcome | Serous impact to the cource of action and outcome | Could result in disaster
PROBABILITY | Low Probability | LOW | MEDIUM | MEDIUM | HIGH
| Risk is unlikely to occur | 1 | 4 | 6 | 10
| Medium Probability | LOW | MEDIUM | HIGH | EXTREME
| Risk will likely occur | 2 | 5 | 8 | 11
| High Probability | MEDIUM | HIGH | HIGH | EXTREME
| Risk will occur | 3 | 7 | 9 | 12
Source GOE FP [1-3]
Refernces
[1] | European Commission. Project Cycle Management Guidelines. Brussels, 2004.
[2] | Datta S, Mukherjee S, editors. Developing a risk management matrix for effective project planning--an empirical study. 2001: Project Management Institute.
[3] | Chapman C, Ward S. Project risk management: processes, techniques, and insights: Wiley; 2003.

## Tool 38Risk Management Template
Tool 38: Risk management template
This template is designed to help users manage the identified and assessed risks (see Tool 37) related to the implementation of a cross-border collaboration project. The template is available in Excel format.
Risk Management Project Flow
*Please fill in based on the matrix results (Tool 37)
Risk definition |  |  |  |  | Stakeholder definiton |  | Risk prioritization and mitigation |  |  |  |  | Risk Post-Assessment
Risk | Risk impact* | Probability* | Risk Level* | Risk Rating Key* | Organisation | Name | Prevention strategy | Mitigation strategy | Reaction according to risk rating key | Application of prevention/mitigation strategy | Rating of prevention/mitigation strategy | Supporting factors of risk prevention/ mitigation process | Hindering factors of risk prevention/ mitigation process | Best practice advice
e.g. human resources (broad definition, could be further specified) | tolerable | medium | medium(5) | medium ALARP | Organisation XY | Mr/Ms XY | thorough HR planning, personnel turnover | replacement of personnel with similar qualifications | reaction depending on risk occurence, immediate reaction in case of risk occurence | yes/no; depending on the project flow | e.g. highly successful, successful, medium successful, slightly successful, not successful | e.g. predefinition of potential successors with related qualification profile | e.g. unavailability of successor, successor with non-equal qualification profile | (depending on the project outcome, e.g. predefinition of successor allowed for a quick replacement with minimal project delays)
Risk Management Post-Assessment
Risk Management Monitoring
Risk Management Pre-Assessment